## MyPlan
Sub Stream | Activity | Activity Category | Activity Type | Start Date | End Date | Owner | State | Notes
Pricing Optimization |  | AFU | Task | 2024-07-01 | 2024-07-31
Pricing Optimization |  | AFU | Milestone | 2024-07-31
Pricing Optimization |  | ATE | Task | 2024-07-31 | 2024-08-30
Pricing Optimization |  | ATE | Milestone | 2024-08-30
Pricing Optimization |  | Sviluppi | Task | 2024-08-15 | 2024-09-30
Pricing Optimization |  | System Test | Task | 2024-09-01 | 2024-09-30
Pricing Optimization |  | UAT | Task | 2024-09-30 | 2024-11-01
Pricing Optimization |  | Rilascio in produzione | Milestone | 2024-11-01