## MyPlan
Sub Stream | Activity | Activity Category | Activity Type | Start Date | End Date | Owner | State | Notes
Pricing Optimization |  | AFU | Task | 2024-07-01 | 2024-07-31
Pricing Optimization |  | AFU | Milestone | 2024-07-31
Pricing Optimization |  | ATE | Task | 2024-07-31 | 2024-08-30
Pricing Optimization |  | ATE | Milestone | 2024-08-30
Pricing Optimization |  | Sviluppi | Task | 2024-08-15 | 2024-09-30
Pricing Optimization |  | System Test | Task | 2024-09-01 | 2024-09-30
Pricing Optimization |  | UAT | Task | 2024-09-30 | 2024-11-01
Pricing Optimization |  | Rilascio in produzione | Milestone | 2024-11-01

## Allocations
Persone | Attività | Stream | Activity Type | Mese-Anno | Anno | Giornate | Note | Check Allocazione Nel Piano | Start Date | End Date
Mario | Requisiti di Accesso - M_Mutui_ATE_Task | Requisiti di Accesso - M | ATE | 2024-09-01 | 2024 | 5 |  | OK | 2024-09-01 | 2024-10-01
Emanuelo | Stream 2 - Sviluppi | Stream 2 | Sviluppi | 2024-09-01 | 2024 | 10 |  | OK | 2024-09-15 | 2024-11-04
Vittoriana | Requisiti di Accesso - M_Mutui_AFU_Task | Requisiti di Accesso - M | AFU | 2024-08-01 | 2024 | 4.4 |  | OK | 2024-08-08 | 2024-09-01